# SASA Applied AI Programme — Curriculum Design Spec V4

Date: 2026-03-23 Client: South African Sugar Association (SASA) Facilitator: Richard [Surname] Status: V4 — Prompt engineering thread added

## Changes from V3

V4 additions: - Prompt engineering woven as an explicit thread across Sessions 1–3: how to structure prompts, build reusable libraries, manage context, and handle large datasets - Session 1 afternoon expanded: prompt anatomy, Claude-specific techniques, prompt library setup - Session 2 morning expanded: prompt reuse patterns, parameterised templates, prompt curation discipline - Session 3 afternoon expanded: context window management, chunking strategies, multi-document prompting, synthesis vs. extraction approaches

## Context (from V3)

Key parameters: - Language: “consulting/building” throughout — Professional Fees budget line - Sessions: 10 (reducible to 8) - Session length: 7 hours (3.5 + lunch/breaks + 3.5) - Location: SASA facility, Mount Edgecombe, in-person - Participants: 15 in-person (11 managers + 3–5 directors) + up to 11 supervisors online - Cadence: approximately every 2 weeks - Claude account: ~$100/month (~R1,700) shared - Technical scope: Python, Node.js, LIMS, Autolab, RAG, large datasets (10 years, multiple centres) - Dave and Sheetal already advanced — use their work throughout as examples - IT meeting pending re: local AI infrastructure (16 GB RAM minimum) - Paperwork deadline: Wednesday 25 March 2026

## Audience

- In-person: 11 managers + 3–5 directors (~15 total)

- Remote: Up to 11 supervisors joining selected sessions

- Technical level: Mixed — Dave and Sheetal already building dashboards and analysis; others less engaged

- Approach: Advanced members contribute as context demonstrators; others build at their level — all in the same room

## Pain Points Being Addressed

- Manual report commentary repeated every cycle

- R7106 and multi-centre historical data (10 years) difficult to query and synthesise

- LIMS exception detection relies on manual review of lengthy reports

- Autolab instrument data not connected to any alerting system

- No AI embedded in source systems — AI used only after export

- SharePoint adequate for documents; insufficient for AI integration

## Curriculum Philosophy

Core principle: Every session produces a working deliverable using SASA’s actual data. No synthetic examples.

Prompt Engineering Thread: Sessions 1–3 carry a deliberate prompt engineering track. This is not a standalone topic — it is embedded in real tasks. By Session 3, every participant has a personal prompt library, understands how to manage context, and can adapt prompt patterns to new problems without starting from scratch.

Pacing: - Sessions 1–3: Data foundations + prompt literacy - Sessions 4–6: Technical capability + local infrastructure - Sessions 7–8: SASA-specific system integrations (LIMS, Autolab, agents) - Sessions 9–10: Production deployment + institutionalisation

Hybrid access: Sessions 3, 5, and 8 are most self-contained for online supervisors. Each session opens with a 15-minute synthesis of the previous session’s output.

Catch-up provision: All outputs stored in shared SASA consulting log (SharePoint). Missed sessions → review deliverables and re-engage.

Language discipline: All deliverables framed as “built” or “specified”. Invoices and materials reference “Applied AI Consulting” and “integration development”.

## Session Structure (7 hours)

| Time | Block |
| --- | --- |
| 09:00–12:30 | Morning block (3.5 hrs, one break included) |
| 12:30–13:30 | Lunch |
| 13:30–17:00 | Afternoon block (3.5 hrs, one break included) |

Structure within blocks is flexible based on work in progress.

## Session Designs

### Session 1 — Foundations Audit, Strategic Framing & Prompt Foundations

Morning: - Review AI work already done by Dave and Sheetal — present as the benchmark, not the exception - Map SASA’s data landscape: R7106 records, LIMS exports, Autolab CSVs, multi-centre historical data, mill reports - Identify datasets with highest integration potential and operational friction - Configure tooling: Claude Pro shared account, Copilot licence review, desktop setup for all attendees

Afternoon: - Prompt Engineering Foundations block (90 min): - Prompt anatomy: role, context, task, format (RCTF) — build SASA’s first template together using actual report language - Claude-specific techniques: how XML tags improve output structure; how to use the 200K token context window for long documents; Projects vs. conversations; system prompts and their purpose - Prompt iteration workflow: draft → test → refine → save — treating prompts as living documents, not one-off queries - Common failure modes: vague instructions, missing context, format not specified — diagnose from real examples - Define programme capstone goals as a group — agreed integration targets that all sessions build toward - Establish shared SASA prompt library in SharePoint: naming conventions, categories, who adds and validates entries, version discipline - Set up shared consulting log: folder structure, naming conventions, access for online attendees

Deliverable: SASA data & systems map + integration targets document + consulting log + seed prompt library (10–15 entries)

### Session 2 — Excel as a Data Engineering Surface

Morning: - Rebuild one real SASA Excel report using Claude as live co-pilot - Structured data principles: column naming, type consistency, AI-readable format - Prompt reuse patterns (45 min): - Parameterised prompt templates vs. fixed prompts — how to build a prompt someone else can run and get the same result - Excel prompt library: summarise, flag exceptions, extract trends, compare periods — one reusable template per use case - Prompt curation discipline: when to adapt a prompt vs. write fresh; how to version prompts that work; avoiding prompt drift across the team - Add validated Excel prompts to SASA shared prompt library

Afternoon: - Apply Microsoft Copilot Excel integration to same dataset — compare outputs, establish workflow preference - Design exception-flagging template for one reporting area (e.g., lab results outside control limits) - Document workflow for supervisor-level operation — the “how to use this prompt” guide

Deliverable: Rebuilt AI-augmented Excel report + exception-flagging template + Excel prompt library (10+ entries in shared library)

### Session 3 — Working with Large Datasets, RAG & Context Management

Morning: - Introduce RAG (Retrieval Augmented Generation): the AI-as-librarian pattern — practical analogy, no code required - Work with SASA multi-year multi-centre data: slice, filter, summarise using Claude with structured exports - Surface data structural problems that limit AI effectiveness

Afternoon: - Context management and large dataset prompting (90 min): - Understanding the context window: Claude’s 200K token capacity in practice — what fits, what doesn’t, what happens at the boundary - When to paste vs. chunk vs. use RAG: decision framework for SASA’s different data types (mill reports, LIMS exports, Autolab CSVs, 10-year historical sets) - Chunking strategies: how to split a large dataset and ask questions across chunks without losing coherence between answers - Summarisation chains: building a prompt sequence that compresses 10-year data into a structured briefing without losing the outliers - Prompting for synthesis vs. extraction: “what does this mean” vs. “find the anomalies” require different prompt structures — practice with SASA data - Multi-document prompting: how to structure queries across multiple SASA data sources in a single conversation; labelling conventions that keep Claude oriented - Build simple document index: SharePoint metadata or structured naming for targeted AI queries - Design SASA data-preparation checklist for LIMS, Autolab, and mill report formats

Deliverable: SASA data-preparation checklist + working RAG demonstration + context management reference card for team

Note for online supervisors: This session is high-value to join — the RAG concept, context management guide, and data checklist apply directly to all roles.

### Session 4 — Python & Node.js as Integration Glue

Morning: - Consulting frame: managers direct and review code, AI writes it — session builds that literacy - Build a real Python data pipeline with AI assistance: LIMS export → transformation → flagged output - Introduce Node.js contrast: Python for data; Node.js for API/web connectors to SharePoint and source systems

Afternoon: - Build pipeline stub: LIMS export → Python → formatted Excel/JSON output - Introduce version control thinking for AI-generated code - Each participant identifies one repetitive data task for automation (inputs for Sessions 7–8)

Prerequisite: Python and Node.js must be pre-installed. IT support required.

Deliverable: Working LIMS-to-output data pipeline stub + automation candidate list per team area

### Session 5 — PowerPoint, Reporting & AI-Generated Narratives

Morning: - Audit reporting burden: hours per week writing the same interpretive text — ROI conversation for directors - Build repeatable narrative workflow: structured data → Claude prompt → draft → human review → sign-off - Apply to one actual SASA periodic report

Afternoon: - Use Copilot PowerPoint integration to generate slides from a SASA data summary — refine via prompt iteration - Design report commentary template: SASA house style, regulatory language, exception conventions encoded - Produce one complete AI-assisted report draft from real data — something a director reviews in-session

Deliverable: AI-assisted SASA report draft + reusable report commentary prompt template

### Session 6 — Running AI on SASA Infrastructure

Morning: - Open with IT meeting findings — map against Session 3 data boundary decisions - Install and configure local AI model on SASA server (with IT present if possible) - Walk through Ollama server mode + Open WebUI browser access — no software on individual machines

Afternoon: - Design SASA data governance framework: cloud vs. on-premise classification — one-page policy for director sign-off - Build local RAG demonstration: index SASA internal documents, query without internet - Establish hosting and maintenance model: ownership, upgrade path, relation to SharePoint

Server minimum spec: - 16 GB RAM (32 GB recommended) - Modern CPU (i7/Ryzen 7+) - Dedicated GPU with 4+ GB VRAM (12 GB recommended for 7B models) - 50 GB free SSD storage - Network-accessible, preferably wired

Deliverable: Local AI server operational + SASA data governance policy document

### Session 7 — LIMS & Autolab Integration

Morning: - Map LIMS data flow end to end: entry → review → exception detection → reporting - Define business rules with laboratory managers - Build AI-assisted exception detection layer: Python script or prompt chain flagging out-of-spec results

Afternoon: - Design notification architecture: exception detected → channel (email/Teams/SharePoint) → alert content - Address Autolab: map where AI intercepts instrument data upstream of LIMS (calibration drift, anomaly detection) - Produce written integration specification: a brief IT can implement independently

Deliverable: LIMS exception detection workflow + Autolab integration specification document

### Session 8 — Agentic Workflows & Automation Pipelines

Morning: - Distinguish prompt from agent: multi-step autonomous decision-making — use LIMS exception workflow from Session 7 as reference - Build multi-step agentic workflow: data arrives → AI checks rules → exception detected → draft alert → human reviews → acts - Introduce tool use and function calling: specific capabilities without unrestricted access

Afternoon: - Design failure modes and human override: safe failure, correct escalation, audit trail - Each participant maps one workflow for conversion to agentic exception flagging - Begin building one selected workflow end-to-end

Pre-built n8n scaffold provided. Attendees configure and extend rather than build from scratch. Pre-configured Ollama connection available if Session 6 server not yet in place.

Minimum viable outcome: One working end-to-end run with real or representative data before session ends.

Deliverable: Working agentic exception-flagging workflow + automation pipeline maps per team area

### Session 9 — Source System Integration & Production Deployment

Morning: - Build functional integration prototypes from Session 8 maps: real data, real rules, real output channels - Build lightweight API connector (Node.js or Python, AI-generated): SASA AI layer ↔ source system without manual exports - Address SharePoint role: document/notification layer vs. integration pattern

Afternoon: - Review Autolab-to-LIMS chain with prototypes in hand — partial live implementation where feasible - Produce SASA AI architecture diagram: which systems talk to which AI layer, what data moves where, what humans approve - Document deployment checklist: what each integration requires to go live

Deliverable: Working integration prototypes + SASA AI architecture diagram

### Session 10 — Capstone Review, Governance & Roadmap

Morning (showcase): - 09:00–09:30: Finish and tidy work from sessions 1–9 - 09:30–11:00: Demos — each participant/team presents their deliverable (5 min each; directors present) - 11:00–11:15: Break - 11:15–12:30: Structured review vs. Session 1 targets — what was built, what remains, why

Afternoon (governance + roadmap): - Build SASA AI governance framework: acceptable use, data classification, prompt library ownership, model maintenance - Design ongoing operating model: who maintains what, how new use cases are prioritised - Address skills continuity: which roles need deep capability (Dave/Sheetal tier), which need operational literacy - 12-month roadmap exercise: 3–5 integration targets, sequenced by value and complexity, with owners and effort

Deliverable: AI governance framework + 12-month integration roadmap + individual 90-day action plans

## Deliverables Summary

| Session | Deliverable |
| --- | --- |
| 1 | SASA data & systems map + integration targets + consulting log + seed prompt library |
| 2 | AI-augmented Excel report + exception-flagging template + Excel prompt library |
| 3 | Data-preparation checklist + RAG demonstration + context management reference card |
| 4 | LIMS-to-output data pipeline stub + automation candidate list |
| 5 | AI-assisted report draft + report commentary template |
| 6 | Local AI server operational + data governance policy |
| 7 | LIMS exception detection workflow + Autolab integration spec |
| 8 | Agentic exception-flagging workflow + automation pipeline maps |
| 9 | Integration prototypes + SASA AI architecture diagram |
| 10 | Governance framework + 12-month roadmap + 90-day action plans |

## Quote Summary

| Option | Sessions | Rate | Subtotal | VAT (15%) | Total |
| --- | --- | --- | --- | --- | --- |
| Full programme | 10 | R3,500 | R35,000 | R5,250 | R40,250 |
| Reduced (if needed) | 8 | R3,500 | R28,000 | R4,200 | R32,200 |

Sessions 9–10 deferred in the 8-session option.

## Prerequisites

Before Session 1: - [ ] Claude Pro shared account set up and access distributed to all attendees - [ ] Attendee machines have admin rights for software installation - [ ] Projector and screen on-site + video conferencing link for remote participants - [ ] SharePoint location established for consulting log and prompt library - [ ] Richard reviews Dave and Sheetal’s existing AI work before this session

Before Session 4: - [ ] Python 3.x pre-installed on all attendee machines (IT support) - [ ] Node.js LTS pre-installed on all attendee machines (IT support) - [ ] VS Code pre-installed - [ ] Git (basic) installed for script version management

Before Session 6: - [ ] IT meeting completed; infrastructure findings available - [ ] Dedicated AI server available on local network (see spec above) - [ ] Ollama pre-installed on server - [ ] Chosen model pre-downloaded on server (Llama 3 ~4 GB, Mistral ~4 GB, Phi-3 ~2 GB)

All sessions: - [ ] Sample or live SASA data available per session topic

## Tools Reference

| Tool | Sessions | Cost | Purpose |
| --- | --- | --- | --- |
| Claude.ai (Pro shared) | 1–5, 7–10 | ~R1,700/mo | Primary AI assistant + Excel/PowerPoint integration (excluded from S6 — offline) |
| Microsoft Copilot | 2, 5 | Included in M365 | In-Office AI for Excel and PowerPoint |
| Python | 3, 4, 6–9 | Free | Data transformation and pipeline scripting |
| Node.js | 4, 9 | Free | API connectors and web-facing integrations |
| VS Code | 4, 7–9 | Free | Code review and management |
| Windsurf IDE | 4 | Free tier | AI-powered code editor |
| Claude Code CLI | 4 | Free | Terminal-based AI coding |
| Ollama | 6–9 | Free, open-source | Local AI model runtime on SASA server |
| Open WebUI | 6–9 | Free, open-source | Browser interface to local AI server |
| n8n | 8, 9 | Free, open-source | Agentic workflow automation (self-hosted) |
| MCP (Model Context Protocol) | 8, 9 | Free | Claude tool connections to files, APIs, systems |

## IT Meeting Prep Notes

Key topics to cover with SASA IT: - Server specification for local AI (see spec above — 16 GB RAM minimum confirmed) - LIMS API access or export format for integration work in Session 7 - Autolab data export format and frequency - SharePoint current architecture — what integration points exist - Python and Node.js installation approval for attendee machines - Network architecture: can the AI server be reached by all attendee machines on the same LAN? - Data security policy — what data can go to Claude Pro vs. must stay on-premise - Claude licensing approval timeline (Richard to send licensing info before this meeting)